## query (24)
MotherProject | Category | Title | Progress Percent | Notes | Priority | Labels | End | Status | MyMotherProjects | Assigned to | Include in Leader Update | Support Request | Collaborators | Description | Scheduled | Start | Shared document | Rich Text Notes | Is Recurring | ID | Link2Mother | MotherProject:Link2Item | Project Phase | Tracking Ticket | Modified By | Modified | Item Type | Path
Z: Projects |  | Store Validation | 0% |  | Low | Intake Hub | 2026-01-30 | Not started |  | Kendall Rush | TRUE |  |  |  | FALSE | 2024-09-23 |  |  | FALSE | 545 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Kendall Rush | 2025-10-09 11:52 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Auto Feed Data on Big Query | 20% |  | High | Auto Feeds | 2026-01-30 | In progress |  | Kendall Rush | TRUE |  |  | Creating a Big Query location to create a flow that allows data to update and then feed to QB. | FALSE | 2024-10-10 |  |  | FALSE | 673 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Kendall Rush | 2025-10-28 07:41 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Auto Feed AMP 2.0 Data updates Q4 | 10% |  |  | Auto Feeds | 2026-01-30 | Not started |  | Kendall Rush | TRUE |  |  | Need to address some issues with Data between Cosmo and AMP, and QB. | FALSE | 2025-11-01 |  |  | FALSE | 692 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Adobe Analytics - Direct Data Source | 25% | Response from Service ticket. To my knowledge, there isn't yet a way to directly access your Adobe data within Tableau. However, some connectors have been developed to facilitate this process. Daexus is a free connector (https://www.daexus.io/products/) that runs locally on your machine, ensuring that no third-party servers access your data, enhancing security. While I'm unsure whether it's Walmart-approved, I recommend contacting IT department for confirmation before using it. Himalay Patel on 16/Feb/24 10:22 AM | Intermediate | Adobe Analytics | 2026-01-30 | In progress |  | Kendall Rush | TRUE |  | Robert Isaacs;#556 | Need to get direct Data Access instead of reports. | FALSE | 2024-10-17 |  |  | FALSE | 694 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Kendall Rush | 2025-10-28 07:41 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Core Work |  | Modular Balancing Auto Request | 15% |  |  | Core Work Team | 2026-01-30 | In progress |  | Kendall Rush | TRUE |  | Brett Weir;#30;#Robert Isaacs;#556;#Randi Roberts;#13 | Ability to generate request based on parameters set by Brett for balancing the modular relays, that are influenced by Merchant and Business request. | FALSE | 2024-11-06 |  |  | FALSE | 743 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Kendall Rush | 2025-10-28 07:41 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Core Work |  | Modular Relay Balancing Automation - Confluence | 10% |  |  | Tableau | 2026-01-30 | In progress |  | Kendall Rush | TRUE |  | Brett Weir;#30;#Robert Isaacs;#556 | Capturing information pertaining to Phase 1 of this project. | FALSE | 2024-11-07 | https://confluence.walmart.com/x/_FCPl | GitHub Repo: https://github.com/robertisaacs-hash/modular_balancing/tree/main | FALSE | 753 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> | 1 |  | Kendall Rush | 2025-10-28 07:41 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Z: Projects |  | Intake Hub Phase 3.0 | 10% |  | High | Intake Hub | 2026-01-30 | In progress |  | Kendall Rush | TRUE |  | Kristii Buttrey;#146;#Randi Roberts;#13;#Robert Isaacs;#556 | Cloned 01/25/2025 05:51 by Kendall Rush. Cloned from task Intake Hub Phase 2: "" | FALSE | 2025-07-26 |  |  | FALSE | 990 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Kendall Rush | 2025-10-28 07:41 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Me @ Inbox 4ITB | 0% |  | Intermediate | Meeting | 2026-01-30 | In progress |  | Kendall Rush | TRUE |  |  |  | FALSE | 2025-02-10 |  |  | TRUE | 1050 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP 2.0 Meeting | 75% |  | Intermediate | AMP | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  |  | FALSE | 2025-02-01 |  |  | TRUE | 1129 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Audience Updates - Roles/Teams FY26 | 50% |  | High | AMP | 2025-10-31 | Blocked |  | Kendall Rush | TRUE | FALSE |  | Cloned 02/28/2025 21:37 by Kendall Rush. Cloned from task Audience Updates - Roles/Teams FY26: "Need to finalize the Future Roles/Teams area for AMP 2.0 updates for FY26. " | FALSE | 2025-02-18 |  |  | FALSE | 1176 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  |  | Kendall Rush | 2025-10-28 07:39 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Core Work |  | Activity Tracking - AMP | 0% | -PM - talk to Randi -Prep Workflow for AMP Task -BQ Table for AMP Task -Dataiku to ML -? | Intermediate | Tableau | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE | Robert Isaacs;#556 | Capturing Task from AMP to add to the Tracker | FALSE | 2025-03-20 |  |  | FALSE | 1213 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-09 11:53 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Core Work |  | Activity Tracking - Intake Hub | 0% | -PM - talk to Randi -Prep Workflow for AMP Task -BQ Table for AMP Task -Dataiku to ML -? | Intermediate | Tableau | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE | Robert Isaacs;#556 | Capturing Task from Intake Hub to add to the Tracker. | FALSE | 2025-03-20 |  |  | FALSE | 1214 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-09 11:53 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Repository - | 0% | Confluence Summary Workflow Locations Desktop Locations Published Locations Server Location & Schedules GitHub Information On-Going Updates & Timing | High | Confluence | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  |  | FALSE | 2025-03-20 |  |  | FALSE | 1215 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Repository - AMP 1.0 | 10% | Confluence Summary Workflow Locations Desktop Locations Published Locations Server Location & Schedules GitHub Information On-Going Updates & Timing | High | Confluence | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | All information around AMP 1.0 Data. | FALSE | 2025-03-20 |  |  | FALSE | 1216 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Repository - AMP 2.0 | 0% | Confluence Summary Workflow Locations Desktop Locations Published Locations Server Location & Schedules GitHub Information On-Going Updates & Timing | High | Confluence | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | All data for AMP 2.0. | FALSE | 2025-03-20 |  |  | FALSE | 1217 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Repository - MM & Playbook | 0% | Confluence Summary Workflow Locations Desktop Locations Published Locations Server Location & Schedules GitHub Information On-Going Updates & Timing | High | Confluence | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | Cloned 03/20/2025 15:21 by Kendall Rush. Cloned from task Repository - : "" | FALSE | 2025-03-20 |  |  | FALSE | 1219 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Z: Projects |  | Repository - Intake Hub | 0% | Confluence Summary Workflow Locations Desktop Locations Published Locations Server Location & Schedules GitHub Information On-Going Updates & Timing | High | Confluence | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | All Data related to Intake Hub | FALSE | 2025-03-20 |  |  | FALSE | 1220 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP 2.0 - DM - Repository - Cloned Task | 0% | Confluence Summary Workflow Locations Desktop Locations Published Locations Server Location & Schedules GitHub Information On-Going Updates & Timing | High | Confluence | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | Cloned 03/20/2025 15:50 by Kendall Rush. Cloned from task Repository - : "" | FALSE | 2025-03-20 |  |  | FALSE | 1221 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:58 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP Beta for My Walmart Beta | 50% |  | High | AMP | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | Created the visual for the AMP CMS message template for the updated needed to test the Beta in September | FALSE | 2025-05-01 |  |  | FALSE | 1331 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:57 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | 4ITB - Weekly | 75% |  | High | AMP | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  |  | FALSE | 2025-02-01 |  |  | TRUE | 1343 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:57 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Z: Core Analytics Team - PM |  | EOC - Hub | 25% | Event Criteria - the information you normally need or want to take about each event. • Event Name – This will be assigned at the beginning of each event. For Hurricanes it will start when the storm is named. • Store – Will need update each store individually • Event Start Date – Will use the date that we are first activated • Event End Date – Will use the date of the last day of activation • Event Type (hurricane, tornado, etc) o Hurricane o Tornado o Severe Weather o Flood o Wildfire o Fire o Arson o Winter Weather o Civil Unrest o Protest o Loss of Infrastructure o Police Activity o Volcano • Store – Will need update each store individually Event Service Updates • Event Name • ESF Team/# o ESF1 – People o ESF2 – Ops Support o ESF3 – Emergency Management o ESF4 – Facilities Services o ESF5 – Merchandise o ESF6 – Supply Chain o ESF7 – AP o ESF8 – Tech o ESF9 – Corp Affairs o ESF10 – Walmart.org • Service Type ( text Field, so they can input anything) • Service Update Title • Service Update Details • Service Update Timestamp | High | Core Work Team | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE | Paul Nelson - EOC;#540;#Chris Sanders;#557;#Robert Isaacs;#556 | Creating a suite of work, that will allow users to input EOC events, Services and updates for those events and Store affected. Which will then feed Dashboard for visual outputs and Auto Feeds for Store Communications. | FALSE | 2025-06-25 |  | Requestor: Kendall Rush On behalf of: Paul Nelson Team: EOC Goal: Provide a dashboard that allows the business to see all the resources for the current EOC events. Details: A place to see all the resources and updates for EOC Events for each E event team. Preferred due date:2025-06-01 Drop Dead date: 2025-07-25 Product count: Estimated days: Project Size: | FALSE | 1379 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:38 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP 2.0 - DM - AD Group Approvals | 75% |  | High | AMP | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | Approvals for AMP AD Groups. | FALSE | 2025-02-01 |  |  | TRUE | 1500 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Robert Isaacs | 2025-10-17 09:57 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Service Now Ticket - Vest | 0% |  |  | Core Work Team | 2026-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  |  | FALSE | 2025-10-07 |  |  | FALSE | 1515 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:31 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Z: Personal Development | Planning & Improvement | FY26 Performance & Pay Review | 0% |  | High |  | 2026-01-23 | In progress |  | Kendall Rush | TRUE | FALSE |  |  | FALSE | 2025-11-01 |  | Striving for excellence is a core value at Walmart, and one of the ways we bring that to life is through partnership and accountability between associates and managers. Associates set, update, and work toward their goals, while managers provide feedback, coach, manage performance, and build future capabilities. Working together, associates and managers help drive our culture of growth and development to help grow great careers. Review Cycle Starts Nov. 1 Our annual Performance and Pay review cycle begins Nov. 1, during which your manager will evaluate your performance, and you’ll conclude with a discussion about your performance rating and any pay changes. Here’s what to expect in the coming months and atoolkit of support resources: How to PrepareReview your progress toward your goals with your manager by Oct. 31 and make any changes in the Performance & Pay tool before managers start performance evaluations on Nov. 1. Update Goals Attend a learning session between Nov. 6 - Jan. 13. Join one of seven sessions designed to strengthen your skills and confidence in the performance and pay process. You'll learn practical tips for completing your self-evaluation and guidance to prepare for meaningful conversations with your manager. See the options below and click the link to add a session to your calendar. All times are in CT. November: 6th at 1 p.m.,11th at 7:30 a.m.,12th at 1p.m. (Spanish)December: 4th at 1 p.m.,11th at 11 p.m.January: 13th at 8:30 a.m.,13th at 11 p.m.Complete your self-evaluation between Nov. 1 - Jan. 23. Use this opportunity to showcase your impact, share your perspective, and tell your story. Your input helps shape how your performance is seen. We'll keep you updated throughout the cycle with reminders and next steps. For questions, reach out to your manager or people partner. | FALSE | 1517 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:30 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Z: Core Analytics Team - PM |  | Portal Updates - Q4 | 0% |  | High |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:33 by Kendall Rush. Cloned from task Portal Updates - Q3: "Cloned 10/02/2025 14:59 by Kendall Rush. Cloned from task Portal Updates: "" " | FALSE | 2025-09-01 |  |  | FALSE | 1549 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Z: Projects |  | Intake Hub Phase 3.0 - Updates List P2 - Q4 | 0% |  |  |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:33 by Kendall Rush. Cloned from task Intake Hub Phase 3.0 - Updates List P2: "Created 10/03/2025 17:40 by Kendall Rush from task: Intake Hub Phase 3.0 - Update list" | FALSE | 2025-10-03 |  |  | FALSE | 1550 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Merchant Leadership Dashboard FY26 Q4 | 0% |  | Intermediate |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:33 by Kendall Rush. Cloned from task Merchant Leadership Dashboard FY26 Q3: "Cloned 10/02/2025 14:47 by Kendall Rush. Cloned from task Merchant Leadership Dashboard FY26: "Need to up date Playbook and MM Data for FY25" " | FALSE | 2025-05-01 |  |  | FALSE | 1551 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP 2.0 Reporting Q4 | 0% | Need your help since this is my first one, so I understand the data flow process and what's typical. | High |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:33 by Kendall Rush. Cloned from task AMP 2.0 Reporting Q3: "Cloned 10/02/2025 14:52 by Kendall Rush. Cloned from task AMP 2.0 Reporting Q2: "Cloned 05/28/2025 14:48 by Kendall Rush. Cloned from task AMP 2.0 Reporting Q1: "Cloned 02/28/2025 21:44 by Kendall Rush. Cloned from task AMP 2.0 Reporting Q1: "Creating the Dashboard that will go into AMP 2.0 Reporting." " " " | FALSE | 2025-04-28 |  |  | FALSE | 1552 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | MyWalmart Click Data for MM Q4 | 0% | Merchant Message Activity Type By WK Verification Completions Top Majority Activity Bottom Majority Activity | High |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:34 by Kendall Rush. Cloned from task MyWalmart Click Data for MM Q3: "Cloned 10/02/2025 14:35 by Kendall Rush. Cloned from task MyWalmart Click Data for MM: "Reporting for My Walmart Click Data" " | FALSE | 2025-06-25 |  | Requestor: Kendall Rush On behalf of: Randi Roberts Team: AM&RR - Activity Goal: Data points for current MyWalmart Reporting for MM clicks. Details: Previously Splunk data, transitioned to OpenObserve, had to reset up my reporting for MM clicks. Preferred due date:2025-06-23 Drop Dead date: 2025-06-27 Product count: Estimated days: Project Size: | FALSE | 1554 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | Tableau Desktop Splitting Q4 | 0% |  | High |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:34 by Kendall Rush. Cloned from task Tableau Desktop Splitting Q3: "Cloned 10/02/2025 14:45 by Kendall Rush. Cloned from task Tableau Desktop Splitting: "Cloned 02/28/2025 21:27 by Kendall Rush. Cloned from task Tableau Desktop Splitting: "Need to review some of the Desktop Workbooks and determine what I can split off from each other to make it more efficient long term. " " " | FALSE | 2024-12-03 |  |  | FALSE | 1555 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP 2.0 Data Updates Q4 | 0% | Add User ID - Done New Stores not showing in reporting - 7011 ( Issue in the raw data) Clean up cleans Added Ranking - Done Update Store Data Connection with ELM. - Done | High |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:35 by Kendall Rush. Cloned from task AMP 2.0 Data Updates Q3: "Cloned 10/02/2025 14:18 by Kendall Rush. Cloned from task AMP 2.0 Data Updates: "Cloned 05/28/2025 14:54 by Kendall Rush. Cloned from task AMP 2.0 Data Updates: "These are the updates I'm reviewing for this time period." " " | FALSE | 2025-04-28 |  |  | FALSE | 1556 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:53 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Core Work |  | Operations Review Update Q4 | 0% |  | High |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:35 by Kendall Rush. Cloned from task Operations Review Update Q3: "Cloned 10/02/2025 14:30 by Kendall Rush. Cloned from task Operations Review Update: "Update the Operations Review with the updated branding and some additional links. " " | FALSE | 2025-05-21 |  |  | FALSE | 1557 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | AMP 1.0 Historical - Workflows Q4 | 0% | Need to clone out for each workflow. |  |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:36 by Kendall Rush. Cloned from task AMP 1.0 Historical - Workflows Q3: "Cloned 10/02/2025 14:17 by Kendall Rush. Cloned from task AMP 1.0 Historical - Workflows: "Update and review workflows, ensure they are worded correctly for repository and archiving. " " | FALSE | 2025-04-18 |  |  | FALSE | 1558 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Reporting |  | SC - Facility Activity & Comm Dashboard Updates Q4 | 0% |  | Intermediate |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:36 by Kendall Rush. Cloned from task SC - Facility Activity & Comm Dashboard Updates Q3: "Cloned 10/02/2025 13:57 by Kendall Rush. Cloned from task SC - Facility Activity & Comm Dashboard Updates: "Any Updates for this dashboard. Usually monthly." " | FALSE | 2025-07-15 |  |  | FALSE | 1559 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-04 07:20 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity |  | QB -Auto Feed AMP 2.0 Data updates Q4 | 0% |  |  |  | 2026-01-31 | Not started |  | Kendall Rush | TRUE | FALSE |  | Cloned 10/28/2025 14:36 by Kendall Rush. Cloned from task QB -Auto Feed AMP 2.0 Data updates Q3: "Cloned 10/02/2025 14:17 by Kendall Rush. Cloned from task QB -Auto Feed AMP 2.0 Data updates : "Creating combined flow to show what's in QB and in AMP 2.0" " | FALSE | 2025-02-01 | https://confluence.walmart.com/display/ISDEMIB/Establish+Connectivity+from+Dataiku+to+Google+BigQuery |  | FALSE | 1560 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-10-28 07:51 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Emergency Template in AMP |  | Implementation through Templates Phase 2/3 | 25% |  | Low | AMP | 2027-01-30 | In progress |  | Kendall Rush | TRUE | FALSE | Kelley Koop;#382 | Creating a place inside AMP to allow Emergency Templates to be created, based on a preapproved or semi preapproved templatae. | FALSE | 2026-02-01 |  |  | FALSE | 1605 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-05 11:24 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity Hub | Team Support | Interface for Activity Hub - V1 | 10% | Initial Version Reporting: -Basic Overall Reporting similar to Operation Review but simplified. Portal: -Ability to go to other tools and reporting Search: -Ability to ask an AI Agent about information connected to the platform. Task: Ability to input Task connected to a Intake Hub Project or outside of Intake Hub. Notification: Set up some basic notifications about Intake Hub, AMP and Task. | High | Development;#VS Code;#Support Request | 2026-05-02 | Not started |  | Kendall Rush | TRUE | FALSE |  | This is the Overall Build of the Activity Hub for the first Version. | FALSE | 2025-10-01 |  |  | FALSE | 1606 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-05 11:34 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
Activity Hub |  | Activity Governance - Integration | 10% |  | Intermediate |  | 2027-01-30 | In progress |  | Kendall Rush | TRUE | FALSE |  | Taking the Governance standards for each item and integrating it into the Reporting and Automation of the Activity Hub. | FALSE | 2025-10-01 |  |  | FALSE | 1607 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-05 12:29 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
AMP Enhancements: |  | Templates Ph1 | 10% |  |  | AMP | 2027-01-30 | In progress |  | Kendall Rush | TRUE | FALSE | Matthew Farnworth;#12 |  | FALSE | 2025-10-01 |  |  | FALSE | 1608 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-05 12:56 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
AMP Enhancements: |  | Roles, Teams and Audiences Ph1 | 25% |  | High |  | 2027-01-30 | In progress |  | Kendall Rush | TRUE | FALSE | Matthew Farnworth;#12 |  | FALSE | 2025-10-01 |  |  | FALSE | 1609 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-05 12:56 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker
AMP Enhancements: |  | Actions - for MyWalmart | 20% |  | Low |  | 2025-12-05 | In progress |  | Kendall Rush | TRUE | FALSE | Matthew Farnworth;#12 |  | FALSE | 2025-12-05 |  |  | FALSE | 1610 |  | <a href='https://teams.wal-mart.com/sites/ATCTeamTEST/Lists/Core%20Work%20Projects/DispForm.aspx?ID='>View Item</a> |  | FALSE | Kendall Rush | 2025-12-05 12:56 | Item | sites/ATCTeamTEST/Lists/Core Work Project Tracker